I actually think this is the perfect time to work on these two documents because they will define how every Nisol Discovery workshop is conducted, regardless of whether you use PowerPoint today or the web application tomorrow.

One important suggestion: don't think of the Facilitator Guide as a document. Think of it as the Standard Operating Procedure (SOP) for every consultant representing Nisol Labs.

1. Facilitator Guide (Priority 1)

Purpose

The Facilitator Guide answers one question:

How should a Nisol Labs consultant conduct an AI Discovery Workshop from start to finish?

If another consultant joins Nisol Labs, they should be able to conduct the workshop using only this guide.

Proposed Structure

Section 1 – Workshop Overview

- Objective

- Expected outcomes

- Workshop duration

- Participants

- Deliverables

Section 2 – Pre-Workshop Preparation

Checklist:

✓ NDA signed

✓ Client questionnaire completed

✓ Participants confirmed

✓ Meeting room / Teams link

✓ Laptop and internet

✓ Presentation ready

✓ Nisol Discovery project created

✓ Previous discussions reviewed

Section 3 – Workshop Agenda

| Time | Activity |
| --- | --- |
| 09:00–09:15 | Welcome & Introductions |
| 09:15–09:30 | Workshop Objectives |
| 09:30–10:00 | Business Overview |
| 10:00–11:00 | Department Discovery |
| 11:00–11:15 | Break |
| 11:15–12:00 | AI Opportunities |
| 12:00–12:30 | Prioritization |
| 12:30–01:00 | Next Steps |

Section 4 – Facilitation Techniques

How to ask questions

How to avoid leading questions

How to encourage participation

How to manage dominant personalities

How to capture requirements accurately

Section 5 – Discovery by Department

For each department:

Objectives

Questions

Follow-up questions

Common pain points

Typical AI opportunities

Red flags

Example

Sales

Objective

Understand the lead-to-cash process.

Primary Questions

How are leads generated?

How are proposals created?

Which CRM is used?

Follow-up Questions

How long does proposal creation take?

Who approves pricing?

How many proposals are created each month?

Common AI Opportunities

- Proposal Generator

- Sales Copilot

- Meeting Summaries

- CRM Assistant

Section 6 – AI Readiness Assessment

Explain

How to score

Examples of scores

How to interpret

When to adjust scores

Section 7 – Prioritization Workshop

Teach consultants

Business Value

Complexity

Risk

ROI

Dependencies

Section 8 – Closing the Workshop

Summarize findings

Validate observations

Confirm next steps

Explain deliverables

Section 9 – Post-Workshop

Within 24 hours

Generate report

Review internally

Prepare roadmap

Schedule executive presentation

2. Proposal Template (Priority 2)

This should not be a generic proposal.

It should be generated directly from the Discovery Workshop.

Structure

Cover Page

Nisol Labs

AI Transformation Proposal

Prepared for:

ABC Manufacturing

Prepared by:

Nisol Labs

Executive Summary

Business goals

Key challenges

Workshop findings

Recommended approach

Current State Assessment

Technology

Processes

Data

People

Governance

AI Readiness Score

Include

Radar chart

Overall score

Recommendations

Recommended AI Use Cases

Example

AI Proposal Generator

Business Value

High

Timeline

8 weeks

Estimated ROI

220%

Scope of Work

Phase 1

Discovery

Phase 2

Pilot

Phase 3

Implementation

Phase 4

Hypercare

Deliverables

- AI Solution Blueprint

- AI Models

- APIs

- Training

- Documentation

- Go-live Support

Timeline

Month 1

Month 2

Month 3

Month 4

Team Structure

Program Manager

Solution Architect

AI Engineer

Data Engineer

Frontend Developer

Backend Developer

QA

Commercial Proposal

Fixed Price

OR

Time & Material

Assumptions

Customer responsibilities

Infrastructure

Licenses

Data availability

Risks

Data quality

Change management

Security

Compliance

Next Steps

Approval

Kickoff

Planning

Implementation

One More Document

I think there is one document missing from our toolkit.

Between the Facilitator Guide and the Proposal Template, we need an:

AI Discovery Report

This becomes the formal output of the workshop.

Structure:

- Executive Summary

- Business Objectives

- Current Challenges

- AI Readiness Assessment

- Department Findings

- AI Opportunity Matrix

- Prioritized Use Cases

- ROI Summary

- Transformation Roadmap

- Recommendations

The proposal should reference this report instead of repeating all of its content. This creates a clear flow:

Workshop

↓

AI Discovery Report

↓

Proposal

↓

Implementation

This separation makes each document focused and professional:

- The Facilitator Guide tells consultants how to run the workshop.

- The AI Discovery Report documents what was found.

- The Proposal explains what Nisol Labs recommends delivering and under what commercial terms.

I believe this three-document approach will make your consulting methodology much more structured, reusable, and scalable.