## Cost Calculator
AI Consulting Phase 1 Audit & Roadmap Cost Calculator
Interactive pricing estimator for Independent AI Consultants in India
PARAMETER / INPUT | VALUE / SELECTION | MULTIPLIER / EFFECT | NOTES & GUIDANCE
Consultant Base Daily Rate (₹) | 45000 | 45000 | Standard mid-senior daily rate range: ₹25,000 - ₹75,000
Base Audit Fixed Days | 5 | 5 Days | Minimum effort required for scoping, kickoff & deck setup
Company Size & Scale Tier | Small / Startup (<50 employees) | 1 | Determines organizational alignment & interview complexity
Number of Workflows to Map | 3 | 1.2 Days / Workflow | Adds ~1.2 days per business process mapped
Stakeholders to Interview | 5 | 0.5 Days / Person | Adds ~0.5 days per key stakeholder/department head
Data & Tech Debt Level | Clean SaaS / Cloud APIs | 1.3 | Adjusts effort for data extraction, cleaning & architecture audit
Compliance & Regulatory Complexity | Standard Internal Use | 1.5 | Surcharge for BFSI, Healthcare, PII, SOC2 & security controls
CALCULATED ESTIMATES & OUTPUTS
Total Estimated Effort Days | 12 | Days | Formula: ROUNDUP((Base + Workflows*1.2 + Interviews*0.5) * Scale, 0)
Base Labor Fee Estimate | 540000 | ₹ | Formula: Effort Days * Daily Rate
Technical Debt Surcharge | 162000 | ₹ | Additional effort cost due to data/legacy complexity
Compliance & Risk Surcharge | 270000 | ₹ | Additional cost due to security & regulatory constraints
FINAL RECOMMENDED PHASE 1 FIXED FEE | 1053000 | ₹ | Total Phase 1 Audit & Roadmap Fixed Client Fee (Rounded to ₹1,000)
RECOMMENDED MILESTONE PAYMENT SCHEDULE (SOW)
Milestone 1: Inception & Discovery (30%) | 315900 | ₹ | Upon SOW signing, kickoff & stakeholder interview scheduling
Milestone 2: Draft Audit & Architecture (40%) | 421200 | ₹ | Upon submission of process maps, tech audit & preliminary ROI matrix
Milestone 3: Final 12-24 Mo Roadmap Sign-off (30%) | 315900 | ₹ | Upon delivery of final roadmap deck, vendor matrix & C-suite presentation

## Lookup Tables
Company Size Tier | Multiplier |  | Tech Debt Level | Multiplier | Compliance Level | Multiplier
Small / Startup (<50 employees) | 1 |  | Clean SaaS / Cloud APIs | 1 | Standard Internal Use | 1
Mid-Market (50-300 employees) | 1.4 |  | Hybrid / Messy Data | 1.3 | Regulated / BFSI / PII | 1.35
Enterprise (300+ employees) | 2 |  | Legacy / Siloed ERP | 1.7
Base Daily Rate |  | Number
25000 |  | 1
30000 |  | 2
35000 |  | 3
40000 |  | 4
45000 |  | 5
50000 |  | 6
55000 |  | 7
60000 |  | 8
65000 |  | 9
70000 |  | 10
75000 |  | 0